## 1a
Table 1a: Watershed Control Measures Completed
Project Name | Previous Project Name(s) if Changed | Permittee(s) | Subwatershed | Project Type | Description | Latitude | Longitude | Required Completion Date in WMP | Actual Completion Date | Capital Costs [$] | Cumulative O&M Costs [$] | Funding Source(s) | Project Footprint [Acres] | Drainage Area [Acres] | Projected Storage Capacity in WMP [Acre-feet] | Actual Storage Capacity1 [Acre-feet, 24-hr] | Actual Storage Capacity [Acre-feet] | Cumulative Volume Addressed2 [Acre-feet]
ARS 55th and Atlantic | Not Applicable | Maywood | LA River | Other (specify) | Installation of ARS in catch basin | 33.9911 | -118.185 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
ARS 55th and Atlantic 2 | Not Applicable | Maywood | LA River | Other (specify) | Installation of ARS in catch basin | 33.9911 | -118.185 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
ARS 56th and Mayflower | Not Applicable | Maywood | LA River | Other (specify) | Installation of ARS in catch basin | 33.9897 | -118.1807 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
ARS 59th and Walker | Not Applicable | Maywood | LA River | Other (specify) | Installation of ARS in catch basin | 33.985 | -118.1722 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
ARS King and Randolph | Not Applicable | Maywood | LA River | Other (specify) | Installation of ARS in catch basin | 33.9816 | -118.1843 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
CPS & ARS Installation Project | Catch Basins | Huntington Park | LA River | Other (specify) | Catch Basin Screens (Citywide) | 33.9738 | -118.216 | Not Applicable | 2022-06-30 07:00 | 258000 | 5000 | Not Applicable | 0 | 0 | Not Applicable | 0 | 0 | 0
CPS 52nd and Heliotrope | Not Applicable | Maywood | LA River | Other (specify) | Installation of CPS in catch basin | 33.9896 | -118.1785 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
CPS 54th and Loma Vista | Not Applicable | Maywood | LA River | Other (specify) | Installation of CPS in catch basin | 33.9934 | -118.198 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
CPS 55th and Atlantic | Not Applicable | Maywood | LA River | Other (specify) | Installation of CPS in catch basin | 33.9911 | -118.185 | Not Applicable | 2019-06-26 07:00 | 818.82 | 757.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
CPS 56th and Loma Vista | Not Applicable | Maywood | LA River | Other (specify) | Installation of CPS in catch basin | 33.9916 | -118.1983 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
CPS 57th and Loma Vista | Not Applicable | Maywood | LA River | Other (specify) | Installation of CPS in catch basin | 33.9906 | -118.1984 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
CPS 58th and Atlantic 3 | Not Applicable | Maywood | LA River | Other (specify) | Installation of CPS in catch basin | 33.9882 | -118.1855 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
CPS 58th and Fishburn | Not Applicable | Maywood | LA River | Other (specify) | Installation of ARS in catch basin | 33.9886 | -118.1899 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
CPS 58th and Heliotrope | Not Applicable | Maywood | LA River | Other (specify) | Installation of CPS in catch basin | 33.9875 | -118.1788 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
CPS 59th and Alamo | Not Applicable | Maywood | LA River | Other (specify) | Installation of CPS in catch basin | 33.9851 | -118.1744 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
CPS 61st and Heliotrope 5 | Not Applicable | Maywood | LA River | Other (specify) | Installation of CPS in catch basin | 33.9829 | -118.1794 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
CPS 61st and King 2 | Not Applicable | Maywood | LA River | Other (specify) | Installation of CPS in catch basin | 33.9834 | -118.1839 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
CPS Clarkson and 60th | Not Applicable | Maywood | LA River | Other (specify) | Installation of CPS in catch basin | 33.9856 | -118.187 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
CPS Cudahy and 52nd | Not Applicable | Maywood | LA River | Other (specify) | Installation of CPS in catch basin | 33.9939 | -118.1845 | Not Applicable | 2019-06-26 07:00 | 818.82 | 757.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
CPS Randolph and Alamo | Not Applicable | Maywood | LA River | Other (specify) | Installation of CPS in catch basin | 33.9806 | -118.1751 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
CPS Randolph and Atlantic | Not Applicable | Maywood | LA River | Other (specify) | Installation of CPS in catch basin | 33.9818 | -118.1864 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
CPS Randolph and District | Not Applicable | Maywood | LA River | Other (specify) | Installation of CPS in catch basin | 33.9801 | -118.1703 | Not Applicable | 2019-06-26 07:00 | 818.82 | 757.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
CPS Randolph and Heliotrope 3 | Not Applicable | Maywood | LA River | Other (specify) | Installation of CPS in catch basin | 33.9811 | -118.1797 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
CPS Slauson and Fishburn | Not Applicable | Maywood | LA River | Other (specify) | Installation of CPS in catch basin | 33.9877 | -118.19 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
CPS Slauson and Heliotrope | Not Applicable | Maywood | LA River | Other (specify) | Installation of CPS in catch basin | 33.9866 | -118.1789 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
CPS Slauson and Heliotrope 2 | Not Applicable | Maywood | LA River | Other (specify) | Installation of CPS in catch basin | 33.9866 | -118.1789 | Not Applicable | 2019-06-26 07:00 | 818.82 | 181.5 | Not Applicable | 0 | 4.1 | Not Applicable | 0 | 0 | 0
E.coli Outreach | Not Applicable | Commerce | Not Applicable | Outreach and Conservation Program | Develop targeted E.coli control outreach program and materials | Not Applicable | Not Applicable | Not Applicable | 2022-06-15 07:00 | 1500 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
Extra Space Storage | 6241 Maywood Avenue | Huntington Park | LA River | Other (specify) | Storage Building | 33.9738 | -118.216 | Not Applicable | 2022-01-10 08:00 | 2000000 | 500 | Not Applicable | 1.8 | 1.8 | Not Applicable | 0 | 0 | 0
Football Field at Salt Lake Park | 3401 E Florence Ave | Huntington Park | LA River | Other (specify) | Sports Playing Field | 33.9738 | -118.216 | Not Applicable | 2022-02-01 08:00 | 500000 | 5000 | Not Applicable | 2.5 | 2.5 | Not Applicable | 0 | 0 | 0
Pet Waste City Website Information | Not Applicable | Commerce | Not Applicable | Outreach and Conservation Program | Develop targeted oet waste information of city website or alternatice media | Not Applicable | Not Applicable | Not Applicable | 2015-12-31 08:00 | 380 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
Pet Waste Outreach | Not Applicable | Commerce | Not Applicable | Outreach and Conservation Program | Develop trageted City/SEAACA pet waste outreach materials | Not Applicable | Not Applicable | Not Applicable | 2013-12-31 08:00 | 250 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
PIPP Options | Not Applicable | Commerce | Not Applicable | Other | Access new public information and participation program (PIPP) options | Not Applicable | Not Applicable | Not Applicable | 2017-06-30 07:00 | 2200 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
POC Source Control Alternative Media | Not Applicable | Commerce | Not Applicable | Outreach and Conservation Program | Utilize alternative media to support POC source control program | Not Applicable | Not Applicable | Not Applicable | 2017-06-30 07:00 | 1500 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
Target Store | 5731 Bickett Street | Huntington Park | LA River | Other (specify) | Shopping Store | 33.9901 | -118.216 | Not Applicable | 2022-03-01 08:00 | 5500000 | 1000 | Not Applicable | 5.5 | 5.5 | Not Applicable | 0.25 | 0.22 | 0.33192
Utilize Gateway COG People Assisting the Homeless (PATH) NGO Partnership | N/A | Bell | Not Applicable | Other | Utilize Gateway COG People Assisting the Homeless (PATH) NGO Partnership | Not Applicable | Not Applicable | Not Applicable | 2022-06-30 07:00 | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
Summary of New and Redevelopment Projects | Not Applicable | Bell | LA River | New and Redevelopment | This line item is intended to provide a summary of new and redevelopment projects. Summarized here are 0 new development and 3 redevelopment projects. The values shown here were developed by summing the respective values of 3 new and redevelopment projects in the area covered by this subwatershed and jurisdiction. | Not Applicable | Not Applicable | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | 28.43 | 7.47 | Not Applicable | 256.7018 | 0.621 | 9.5905
Summary of New and Redevelopment Projects | Not Applicable | Commerce | LA River | New and Redevelopment | This line item is intended to provide a summary of new and redevelopment projects. Summarized here are 0 new development and 13 redevelopment projects. The values shown here were developed by summing the respective values of 13 new and redevelopment projects in the area covered by this subwatershed and jurisdiction. | Not Applicable | Not Applicable | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | 518.4092 | 517.15 | Not Applicable | 5005.4725 | 2.6317 | 33.35
Summary of New and Redevelopment Projects | Not Applicable | Commerce | Rio Hondo | New and Redevelopment | This line item is intended to provide a summary of new and redevelopment projects. Summarized here are 0 new development and 5 redevelopment projects. The values shown here were developed by summing the respective values of 5 new and redevelopment projects in the area covered by this subwatershed and jurisdiction. | Not Applicable | Not Applicable | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | 15.35 | 15.01 | Not Applicable | 26.211 | 0.69926 | 16.1693
Summary of New and Redevelopment Projects | Not Applicable | Cudahy | LA River | New and Redevelopment | This line item is intended to provide a summary of new and redevelopment projects. Summarized here are 0 new development and 2 redevelopment projects. The values shown here were developed by summing the respective values of 2 new and redevelopment projects in the area covered by this subwatershed and jurisdiction. | Not Applicable | Not Applicable | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | 9.7 | 6.25 | Not Applicable | 117.3312 | 0 | 0
Summary of New and Redevelopment Projects | Not Applicable | Huntington Park | LA River | New and Redevelopment | This line item is intended to provide a summary of new and redevelopment projects. Summarized here are 1 new development and 4 redevelopment projects. The values shown here were developed by summing the respective values of 5 new and redevelopment projects in the area covered by this subwatershed and jurisdiction. | Not Applicable | Not Applicable | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | 11.6 | 11.6 | Not Applicable | 262.7512 | 0.22 | 2.0666
Summary of New and Redevelopment Projects | Not Applicable | Maywood | LA River | New and Redevelopment | This line item is intended to provide a summary of new and redevelopment projects. Summarized here are 0 new development and 4 redevelopment projects. The values shown here were developed by summing the respective values of 4 new and redevelopment projects in the area covered by this subwatershed and jurisdiction. | Not Applicable | Not Applicable | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | 18.56 | 18.56 | Not Applicable | 417.817 | 1.56 | 26.127
Summary of New and Redevelopment Projects | Not Applicable | Vernon | LA River | New and Redevelopment | This line item is intended to provide a summary of new and redevelopment projects. Summarized here are 0 new development and 37 redevelopment projects. The values shown here were developed by summing the respective values of 37 new and redevelopment projects in the area covered by this subwatershed and jurisdiction. | Not Applicable | Not Applicable | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | 160.85 | 160.85 | Not Applicable | 2148.7981 | 12.89 | 485.7665
[1] Unless provided by the jurisdiction, the 24-hour capacity is a WRAMPS calculated value that is based on the sum of storage capacity, percolation rate, drawdown to the sanitary sewer, and rate of onsite use, as applicable to each project.
[2] Cumulative volume addressed is simulated with WMMS 2.0 using hourly, process-based continuous simulation. The WMMS simulation for each project represents the hourly runoff from the project drainage area into the project and the portion of the inflow that is retained and treated by the project (overflow from the project and bypass are excluded). The simulation for each project begins on the completion date or 12/28/2012, whichever is earlier, and ends on the last day of the reporting period.

## 1b
Table 1b: Watershed Control Measures Planned and In Progress
Project Name | Permittee(s) | Subwatershed | Project Type | Description | Latitude | Longitude | Required Completion Date in WMP | Estimated Completion Date | Estimated Capital Costs [$] | Estimated Annual O&M Costs [$] | Funding Source(s) | Project Footprint [Acres] | Drainage Area [Acres] | Projected Storage Capacity in WMP [Acre-feet] | Status
Access new public information and participation program (PIPP) options | Vernon | Not Applicable | Outreach and Conservation Program | Access new public information and participation program (PIPP) options | Not Applicable | Not Applicable | Not Applicable | 06/30/2016 | 100 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Annually inspect FOG control and disposal equipment | Vernon | Not Applicable | Source Investigation Efforts | Annually inspect FOG control and disposal equipment | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 100 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Annually inspect FOG control and disposal equipment | Bell | Not Applicable | Other | Annually inspect FOG control and disposal equipment | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Annually inspect FOG control and disposal equipment of commercial and food outlets | Cudahy | Not Applicable | Other | Annually inspect FOG control and disposal equipment | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Arterial Medians | Commerce | Not Applicable | Enhanced Street Sweeping | Street vacuum arterial medians | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 210000 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Assist Southeast Regional Mental Health Evaluation Team (SRMET) | Bell | Not Applicable | Other | Assist Southeast Regional Mental Health Evaluation Team (SRMET) | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 43000 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Catch Basin Enhancement | Commerce | Not Applicable | Other | Enhance catch basin full capture device (FCD/CPS) cleaning | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 86000 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Catch Basin Modification | Commerce | Not Applicable | Other | Consider catch basin modification opportunities to allow FCD installation | Not Applicable | Not Applicable | Not Applicable | 06/01/2025 | 868000 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Conduct street sweeping/vacuuming at least once per week | Cudahy | Not Applicable | Enhanced Street Sweeping | Conduct street vacuuming at least once per week | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | 56520 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Conduct street vacuuming at least once per week | Vernon | Not Applicable | Enhanced Street Sweeping | Weekly street vacuuming | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 100 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Conduct street vacuuming at least once per week | Bell | Not Applicable | Enhanced Street Sweeping | Conduct street vacuuming at least once per week. Contract for generative air vacuums. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 66336 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Consider catch basin modification opportunities to allow FCD installation | Vernon | Not Applicable | Other | Consider catch basin modification opportunities to allow FCD installation | Not Applicable | Not Applicable | Not Applicable | 10/31/2015 | 100 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Consider catch basin modification opportunities to allow FCD installation | Bell | Not Applicable | Other | Consider catch basin modification opportunities to allow FCD installation | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Contract for regenerative air street sweeping/vacuuming | Cudahy | Not Applicable | Enhanced Street Sweeping | Contract for regenerative air vacuums | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Contract for regenerative air vacuums | Bell | Not Applicable | Enhanced Street Sweeping | Contract for regenerative air vacuums | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Contract for Regenerative Air Vacuums | Vernon | Not Applicable | Enhanced Street Sweeping | Contract for regenerative air vacuums sweepers | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 100 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Contract for street sweeping/vacuuming at or below 5 MPH with parking enforcement oversight | Cudahy | Not Applicable | Enhanced Street Sweeping | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Contract for Street Sweeping/Vacuuming at or below 5 mph with parking enforcement oversight | Bell | Not Applicable | Enhanced Street Sweeping | Contract for Street Sweeping/Vacuuming at or below 5 mph with parking enforcement oversight | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 170202 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Contract with solid waste franchisee to provide bins limited opening lids of commercial and food outlets | Cudahy | Not Applicable | Other | Modify solid waste disposal contracts to provide limited opening lids | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Develop and enforce impervious surfaces pet waste ordinance | Cudahy | Not Applicable | Other | Utilize Industrial/Commercial (I/C) facility inspectors to identify POCs | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Develop and enforce trash bin source control ordinances of commercial and food outlets | Cudahy | Not Applicable | Other | Enhance enforcement of trash bin closure (E. coli) source controls | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | 5000 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Develop and implement targeted outreach efforts through City/SEAACA | Cudahy | Not Applicable | Outreach and Conservation Program | Enhance Illicit Connection/Discharge (IC/ID) enforcement & follow up | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Develop ordinance controlling pet waste on impervious surfaces | Vernon | Not Applicable | Expanded LID Ordinance | Develop ordinance controlling pet waste on impervious surfaces | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 100 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Develop pollutants of concern (POC) source control outreach program | Cudahy | Not Applicable | Outreach and Conservation Program | Develop ordinace controlling pet waste on impervious surfaces | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Develop pollutants of concern (POC) source control program | Vernon | Not Applicable | Source Investigation Efforts | Develop pollutants of concern (POC) source control program | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 100 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Develop targeted City/SEAACA pet waste outreach materials | Vernon | Not Applicable | Source Investigation Efforts | Develop targeted City/SEAACA pet waste outreach materials | Not Applicable | Not Applicable | Not Applicable | 01/31/2016 | 100 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Develop targeted City/SEAACA pet waste outreach materials | Bell | Not Applicable | Outreach and Conservation Program | Develop targeted City/SEAACA pet waste outreach materials. Develop targeted pet waste information of city website or alternative media. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Develop targeted E. coli control outreach program and materials | Vernon | Not Applicable | Outreach and Conservation Program | Develop targeted E. coli control outreach program and materials | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 100 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Develop targeted outreach effort related to bacterial discharges of commercial and food outlets | Cudahy | Not Applicable | Outreach and Conservation Program | Develop targeted E. coli control outreach program and materials | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Develop targeted pet waste information of city website or alternative media | Bell | Not Applicable | Outreach and Conservation Program | Develop targeted pet waster infromation of city website or alternative media | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
E Coli Control | Maywood | Not Applicable | Outreach and Conservation Program | Targeted E. Coli control outreach program and materials | Not Applicable | Not Applicable | Not Applicable | 12/31/2015 | 1960 | Not Applicable | Municipal General Fund | Not Applicable | Not Applicable | Not Applicable | Implementation
E.coli Source Control | Commerce | Not Applicable | Other | Enhance enforcement of trash bin closure (E.coli) source controls | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 1800 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Enhance catch basin full capture device (FCD/CPS) cleaning | Vernon | Not Applicable | Other | Enhance catch basin full capture device (FCD/CPS) cleaning | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 100 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Enhance catch basin full capture device (FCD/CPS) cleaning | Bell | Not Applicable | Other | Enhance catch basin full capture device (FCD/CPS) cleaning | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Enhance enforcement of trash bin closure (E. coli) source controls | Vernon | Not Applicable | Incentive Program | Enhance enforcement of trash bin closure (E. coli) source controls | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 100 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Enhance IC/ID enforcement & follow up | Vernon | Not Applicable | Source Investigation Efforts | Enhance IC/ID enforcement & follow up | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 100 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Enhance Illicit Connection/Discharge (IC/ID) enforcement & follow up | Bell | Not Applicable | Source Investigation Efforts | Enhance Illicit Connection/Discharge (IC/ID) enforcement & follow up | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Enhance the extent, timing, and/or frequency of catch basin and storm drain cleaning | Cudahy | Not Applicable | Other | Enhance catch basin full capture device (FCD/CPS) cleaning | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | 3000 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Enhanced IDDE Enforcement | Commerce | Not Applicable | Other | Enhanced Illicit Discharge Detection Elimination (IDDE) enforcement and follow up, and identification of IC/ID program opportunities and implementation strategy | Not Applicable | Not Applicable | Not Applicable | 06/30/2016 | 2200 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Enhanced Industrial/Commercial Inspections | Commerce | Not Applicable | Outreach and Conservation Program | Inspectors identify pollutants of concern during routine MS4 Industrial/Commercial Inspections | Not Applicable | Not Applicable | Not Applicable | 09/03/2013 | 100000 | Not Applicable | Safe, Clean Water | Not Applicable | Not Applicable | Not Applicable | Implementation
Expand street sweeping/vacuuming to include arterial medians | Cudahy | Not Applicable | Enhanced Street Sweeping | Street sweeping of arterial medians | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Expand the use of alternative media outlets, including city website for pet waste | Cudahy | Not Applicable | Outreach and Conservation Program | Identify IC/ID program opportunities and consider implementation | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | 5000 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Fat, Oil, and Grease Inspections | Commerce | Not Applicable | Outreach and Conservation Program | Annually inspect FOG control and disposal equipment | Not Applicable | Not Applicable | Not Applicable | 06/30/2015 | 3100 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
FCD and CPS Cleaning | Maywood | Not Applicable | Other | Enhanced catch basin full capture device cleaning | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 12725 | Not Applicable | Safe, Clean Water | Not Applicable | Not Applicable | Not Applicable | Implementation
FOG Control Inspections | Maywood | Not Applicable | Source Investigation Efforts | Annually inspect FOG control and disposal equipment | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 9615 | Not Applicable | Safe, Clean Water | Not Applicable | Not Applicable | Not Applicable | Implementation
Gateway COG PATH NGO Partnership | Commerce | Not Applicable | Outreach and Conservation Program | People Assisting the Homeless (PATH) partnership to reduce homelessness near and around water bodies | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 5000 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Gateway COG PATH NGO Partnership | Commerce | Not Applicable | Other | Utilize COG People Assisting the Homeless (PATH) NGO Partnership | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 5000 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
IC Facility Inspectors | Commerce | Not Applicable | Other | Utilize Industrial/Commercial(I/C) facility inspectors to identify POC's | Not Applicable | Not Applicable | Not Applicable | 06/30/2023 | 125810 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Identify catch basin and storm drain cleaning modification opportunities and consider implementation | Cudahy | Not Applicable | Other | Consider catch basin modification opportunities to allow FCD installation | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Identify cleaning frequency for catch basins with CPS or ARS | Cudahy | Not Applicable | Other | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | 1500 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Identify cleaning frequency for catch basins with CPS or ARS | Bell | Not Applicable | Other | Identify cleaning frequency for catch basins with CPS or ARS | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1000 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Identify IC/ID modification opportunities and consider implementation | Cudahy | Not Applicable | Source Investigation Efforts | Utilize Gateway COG People Assisting the Homeless (PATH)NGO | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Identify IC/ID program opportunities and consider implementation | Vernon | Not Applicable | Source Investigation Efforts | Identify IC/ID program opportunities and consider implementation | Not Applicable | Not Applicable | Not Applicable | 06/30/2016 | 100 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Illicit Connection and Discharge Program | Maywood | Not Applicable | Source Investigation Efforts | Enhance IC/ID enfrocement and follow up, and identify program opportunities for implementation | Not Applicable | Not Applicable | Not Applicable | 12/31/2015 | 0 | Not Applicable | Municipal General Fund | Not Applicable | Not Applicable | Not Applicable | Implementation
Implement enforcement ordinances and prompt follow up inspections for Illicit Connection/Discharge (IC/ID). | Cudahy | Not Applicable | Source Investigation Efforts | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | 5000 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Industrial and Commercial Inspections | Maywood | Not Applicable | Source Investigation Efforts | Utilize Industrial/Commercial (I/C) facility inspectors to identify POCs | Not Applicable | Not Applicable | Not Applicable | 12/31/2015 | 12650 | Not Applicable | Safe, Clean Water | Not Applicable | Not Applicable | Not Applicable | Implementation
Industrial and Commerical Inspections | Maywood | Not Applicable | Source Investigation Efforts | Utilize Industrial/Commercial (I/C) facility inspectors to identify POCs | Not Applicable | Not Applicable | Not Applicable | 12/31/2015 | 36580 | Not Applicable | Safe, Clean Water | Not Applicable | Not Applicable | Not Applicable | Implementation
Industrial/Commercial (I/C) inspectors to provide list of watershed TMDL POCs (e.g. trash, zinc, E.coli bacteria) | Cudahy | Not Applicable | Source Investigation Efforts | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | 15000 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
John Anson Ford Park | Bell Gardens | Rio Hondo | Regional Infiltration Gallery | To build an infiltration Cistern to capture nutrients, heavy metals, bacteria and reduce toxicity from a 2,296 acre watershed area by installing storm water and dry weather infiltration facilities. | 33.9582 | -118.1539 | Not Applicable | 08/25/2023 | Not Applicable | 50000 | Not Applicable | 1.15 | 2295 | Not Applicable | Construction
Modify solid waste disposal contracts to provide limited opening lids | Vernon | Not Applicable | Expanded LID Ordinance | Modify solid waste disposal contracts to provide limited opening lids | Not Applicable | Not Applicable | Not Applicable | 06/30/2016 | 100 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Parking Enforcement | Maywood | Not Applicable | Enhanced Street Sweeping | Utilize parking enforcement to maximize vacuum performance | Not Applicable | Not Applicable | Not Applicable | 12/31/2013 | 33000 | Not Applicable | Municipal General Fund | Not Applicable | Not Applicable | Not Applicable | Implementation
PATH Partnership | Maywood | Not Applicable | Other | Utilize Gateway COG People Assisting the Homeless (PATH) NGO Partnership | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 0 | Not Applicable | Municipal General Fund | Not Applicable | Not Applicable | Not Applicable | Implementation
Pet Waste Ordinance | Maywood | Not Applicable | Other | Develop ordinance controlling pet waste on impervious surfaces | Not Applicable | Not Applicable | Not Applicable | 12/31/2016 | 20000 | Not Applicable | Municipal General Fund | Not Applicable | Not Applicable | Not Applicable | Implementation
Pet Waste Ordinance | Commerce | Not Applicable | Other | Develop ordinance controlling pet waste on impervious surfaces | Not Applicable | Not Applicable | Not Applicable | 12/31/2015 | 800 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Pet Waste Ordinance | Commerce | Not Applicable | Other | Develop and update citywide ordinanance to control pet waste on impervious surfaces | Not Applicable | Not Applicable | Not Applicable | 12/31/2015 | 8067.28 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Pet Waste Outreach | Maywood | Not Applicable | Outreach and Conservation Program | Develop targeted City/SEAACA pet waste outreach materials | Not Applicable | Not Applicable | Not Applicable | 12/31/2016 | 2000 | Not Applicable | Municipal General Fund | Not Applicable | Not Applicable | Not Applicable | Implementation
POC Source Control Program | Commerce | Not Applicable | Other | Develop pollutants of concern (POC) source control program | Not Applicable | Not Applicable | Not Applicable | 06/30/2017 | 3200 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
POC Source Control Program | Maywood | Not Applicable | Outreach and Conservation Program | Develop pollutants of concern (POC) source control program and support through alternative media | Not Applicable | Not Applicable | Not Applicable | 12/31/2015 | 5000 | Not Applicable | Municipal General Fund | Not Applicable | Not Applicable | Not Applicable | Implementation
POC Source Control Program | Commerce | Not Applicable | Other | Develop pollutants of concern source control program | Not Applicable | Not Applicable | Not Applicable | 06/30/2015 | 3200 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Public Information and Participation Program | Maywood | Not Applicable | Outreach and Conservation Program | Access new public information and participiation program (PIPP) options | Not Applicable | Not Applicable | Not Applicable | 12/31/2016 | 310 | Not Applicable | Safe, Clean Water | Not Applicable | Not Applicable | Not Applicable | Implementation
Public Information and Participiation Program | Maywood | Not Applicable | Outreach and Conservation Program | Access new public information and participiation program (PIPP) options | Not Applicable | Not Applicable | Not Applicable | 12/31/2016 | 1960 | Not Applicable | Safe, Clean Water | Not Applicable | Not Applicable | Not Applicable | Implementation
Regenerative Air Vacuums | Commerce | Not Applicable | Enhanced Street Sweeping | Contract for regenerative air vacuums | Not Applicable | Not Applicable | Not Applicable | 10/31/2019 | 210000 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Regenerative Air Vacuums | Maywood | Not Applicable | Enhanced Street Sweeping | Contract for regenerative air vacuums | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 90000 | Not Applicable | Municipal General Fund | Not Applicable | Not Applicable | Not Applicable | Implementation
Rosewood Park | Commerce, Bell, Huntington Park, Cudahy, Maywood, Bell Gardens, Vernon | LA River | Regional Infiltration Gallery | Project to address LAR Bacteria TMDL | 34.0028 | -118.1548 | 03/23/2037 | Not Applicable | 19254428 | 50000 | Not Applicable | 8.5 | 1064 | 31 | Planning
Solid Waste Disposal Contract | Maywood | Not Applicable | Other | Modify solid waste disposal contracts to porivde limited opening lids | Not Applicable | Not Applicable | Not Applicable | 12/31/2015 | 10000 | Not Applicable | Municipal General Fund | Not Applicable | Not Applicable | Not Applicable | Implementation
Street vacuum arterial medians | Vernon | Not Applicable | Enhanced Street Sweeping | Street vacuum arterial medians | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 100 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Street vacuum arterial medians | Bell | Not Applicable | Enhanced Street Sweeping | Street vacuum arterial medians | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 103866 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Street Vacuuming | Maywood | Not Applicable | Enhanced Street Sweeping | Street vacuuming conducted at least once per week | Not Applicable | Not Applicable | Not Applicable | 12/31/2013 | 90000 | Not Applicable | Safe, Clean Water | Not Applicable | Not Applicable | Not Applicable | Implementation
Street Vacuuming | Commerce | Not Applicable | Enhanced Street Sweeping | Conduct street vacuuming at least once per week | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 210000 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Street Vacuuming Parking Enforcement | Commerce | Not Applicable | Other | Utilize parking enforcement to maximize vacuum performance | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 210000 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Study of opportunities to enhance or modify education and outreach program for implementation | Cudahy | Not Applicable | Outreach and Conservation Program | Develop targeted pet waste information of city website or | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Trash Bin Closure Enforcement | Maywood | Not Applicable | Other | Enhanced enforcement of trash bin closure (E. coli) source controls | Not Applicable | Not Applicable | Not Applicable | 03/01/2020 | 2000 | Not Applicable | Municipal General Fund | Not Applicable | Not Applicable | Not Applicable | Implementation
Trash Bin Closure Source Control | Commerce | Not Applicable | Other | Modify solid waste disposal contracts to provide limited opening lids, and enhanced enforcement of trash bin closure (E. coli) source controls | Not Applicable | Not Applicable | Not Applicable | 06/30/2016 | 2400 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Utilize alternative media to support POC source control program | Cudahy | Not Applicable | Outreach and Conservation Program | Develop targeted City/SEAACA pet waste outreach materials | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | 1500 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Utilize alternative media to support POC source control program | Vernon | Not Applicable | Outreach and Conservation Program | Utilize alternative media to support POC source control program | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 100 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Utilize Gateway COG People Assisting the Homeless (PATH) NGO Partnership | Cudahy | Not Applicable | Other | Develop pollutants of concern (POC) source control program | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | 5000 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Utilize Gateway COG People Assisting the Homeless (PATH) NGO Partnership | Vernon | Not Applicable | Incentive Program | Utilize Gateway COG People Assisting the Homeless (PATH) NGO Partnership | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 100 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Utilize I/C facility inspectors to identify POCs | Vernon | Not Applicable | Source Investigation Efforts | Utilize I/C facility inspectors to identify POCs | Not Applicable | Not Applicable | Not Applicable | 12/31/2015 | 100 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Utilize Indutrial/Commercial (I/C) facility inspectors to identify POCs | Bell | Not Applicable | Source Investigation Efforts | Utilize Industrial/Commercial (I/C) facility inspectors to identify POCs | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Utilize parking enforcement to maximize vacuum performance | Vernon | Not Applicable | Enhanced Street Sweeping | Parking enforcement street vacuuming support | Not Applicable | Not Applicable | Not Applicable | 12/28/2012 | 100 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Utilize parking enforcement to maximize vacuum performance | Bell | Not Applicable | Enhanced Street Sweeping | Utilize parking enforcement to maximize vacuum performance | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Utilize signage/parking enforcement to maximize vacuum performance | Cudahy | Not Applicable | Enhanced Street Sweeping | Utilize parking enforcement to maximize vacuum performance | Not Applicable | Not Applicable | Not Applicable | 12/31/2022 | 15000 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Implementation
Veterans Park Yard | Bell Gardens | Rio Hondo | Other (specify) | A reconstruction of the asphalt and drainage for the City Yard in Bell Gardens, ensuring MS4 compliance for the site. | 33.9664 | -118.1458 | Not Applicable | 06/01/2023 | Not Applicable | 50000 | Not Applicable | 0.5 | 0.75 | Not Applicable | Design
Warehouse (Exist) | Huntington Park | LA River | Other (specify) | Self-Storage (Proposed) | 33.9738 | -118.216 | Not Applicable | 06/30/2023 | 1500000 | 1000 | Not Applicable | 3.05 | 3.05 | Not Applicable | Construction
Summary of New and Redevelopment Projects | Bell Gardens | Rio Hondo | New and Redevelopment | This line item is intended to provide a summary of new and redevelopment projects. Summarized here are 0 new development and 1 redevelopment projects. The values shown here were developed by summing the respective values of 1 new and redevelopment projects in the area covered by this subwatershed and jurisdiction. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0.5 | 0.75 | Not Applicable | Not Applicable
Summary of New and Redevelopment Projects | Commerce | LA River | New and Redevelopment | This line item is intended to provide a summary of new and redevelopment projects. Summarized here are 0 new development and 4 redevelopment projects. The values shown here were developed by summing the respective values of 4 new and redevelopment projects in the area covered by this subwatershed and jurisdiction. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 18.1 | 17.38 | Not Applicable | Not Applicable
Summary of New and Redevelopment Projects | Commerce | Rio Hondo | New and Redevelopment | This line item is intended to provide a summary of new and redevelopment projects. Summarized here are 0 new development and 4 redevelopment projects. The values shown here were developed by summing the respective values of 4 new and redevelopment projects in the area covered by this subwatershed and jurisdiction. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 25.5971 | 21.24 | Not Applicable | Not Applicable
Summary of New and Redevelopment Projects | Huntington Park | LA River | New and Redevelopment | This line item is intended to provide a summary of new and redevelopment projects. Summarized here are 0 new development and 1 redevelopment projects. The values shown here were developed by summing the respective values of 1 new and redevelopment projects in the area covered by this subwatershed and jurisdiction. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 3.05 | 3.05 | Not Applicable | Not Applicable
Summary of New and Redevelopment Projects | Vernon | LA River | New and Redevelopment | This line item is intended to provide a summary of new and redevelopment projects. Summarized here are 0 new development and 6 redevelopment projects. The values shown here were developed by summing the respective values of 6 new and redevelopment projects in the area covered by this subwatershed and jurisdiction. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 19.04 | 19.04 | Not Applicable | Not Applicable

## 1c
Table 1c: WBPC Compliance (note: WRAMPS does not currently populate this table - each WMP Group will need to provide the entries manually)
WBPC Category (1, 2, or 3) | Pollutant | Receiving Water | Weather Condition (Wet, Dry, N/A) | Interim or Final | Deadline | Deadline Met? (Yes, No, N/A) | Method of Compliance

## 1.2a
Table 1.2a: Additional Information Regarding Watershed Control Measures Completed
Project Name | Permittee(s) Collaborated with | Non-Permittee(s) Collaborated with | Funding Sought [$] | Funding Obtained [$] | Technical Assistance Received | Provides Clean Streets Benefit (e.g., street sweeping, litter abatement, etc.) ? [Yes/No] | Provides More Parks and Green Spaces Benefit? [Yes/No] | Provides Reduced Heat Island Effect Benefit? [Yes/No] | Provides Reduced Flooding Benefit? [Yes/No] | Provides Water Supply Augmentation Benefit? [Yes/No] | Provides Neighborhood Beautification Benefit? [Yes/No] | Provides Job Creation Benefit? [Yes/No] | Provides Benefits Accruing to Disadvantaged Communities? (as identified on CalEnviroScreen)
ARS 55th and Atlantic | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
ARS 55th and Atlantic 2 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
ARS 56th and Mayflower | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
ARS 59th and Walker | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
ARS King and Randolph | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
CPS & ARS Installation Project | Not Applicable | Not Applicable | 258000 | 258000 | Not Applicable | Yes | Yes | No | No | No | Yes | Yes | Yes
CPS 52nd and Heliotrope | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
CPS 54th and Loma Vista | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
CPS 55th and Atlantic | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
CPS 56th and Loma Vista | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
CPS 57th and Loma Vista | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
CPS 58th and Atlantic 3 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
CPS 58th and Fishburn | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
CPS 58th and Heliotrope | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
CPS 59th and Alamo | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
CPS 61st and Heliotrope 5 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
CPS 61st and King 2 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
CPS Clarkson and 60th | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
CPS Cudahy and 52nd | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
CPS Randolph and Alamo | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
CPS Randolph and Atlantic | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
CPS Randolph and District | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
CPS Randolph and Heliotrope 3 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
CPS Slauson and Fishburn | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
CPS Slauson and Heliotrope | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
CPS Slauson and Heliotrope 2 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | No | No
E.coli Outreach | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | No | No | No | No | No | No | No | No
Extra Space Storage | Not Applicable | Not Applicable | 0 | 0 | Not Applicable | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Football Field at Salt Lake Park | Not Applicable | Not Applicable | 0 | 0 | Not Applicable | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Pet Waste City Website Information | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | No | No | No | No | No | No | No | No
Pet Waste Outreach | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | No
PIPP Options | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | No | No | No | No | No | No | No | No
POC Source Control Alternative Media | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | No | No | No | No | No | No | No | No
Target Store | Not Applicable | Not Applicable | 0 | 0 | Not Applicable | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Utilize Gateway COG People Assisting the Homeless (PATH) NGO Partnership | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes

## 1.3a
Table 1.3a: Additional Information Regarding Watershed Control Measures Planned and In Progress
Project Name | Permittee(s) Collaborated with | Non-Permittee(s) Collaborated with | Funding Sought [$] | Funding Obtained [$] | Technical Assistance Received | Provides Clean Streets Benefit (e.g., street sweeping, litter abatement, etc.) ? [Yes/No] | Provides More Parks and Green Spaces Benefit? [Yes/No] | Provides Reduced Heat Island Effect Benefit? [Yes/No] | Provides Reduced Flooding Benefit? [Yes/No] | Provides Water Supply Augmentation Benefit? [Yes/No] | Provides Neighborhood Beautification Benefit? [Yes/No] | Provides Job Creation Benefit? [Yes/No] | Provides Benefits Accruing to Disadvantaged Communities? (as identified on CalEnviroScreen)
Access new public information and participation program (PIPP) options | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | No | Yes
Annually inspect FOG control and disposal equipment | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | Yes | Yes
Annually inspect FOG control and disposal equipment | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | No | No | No | No | No | No | No | Yes
Annually inspect FOG control and disposal equipment of commercial and food outlets | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes
Arterial Medians | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | Yes | No | No
Assist Southeast Regional Mental Health Evaluation Team (SRMET) | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | No | No | No | No | No | No | No | Yes
Catch Basin Enhancement | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | Yes | No | No
Catch Basin Modification | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | Yes | No | No
Conduct street sweeping/vacuuming at least once per week | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | Yes | No | Yes
Conduct street vacuuming at least once per week | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | Yes | Yes
Conduct street vacuuming at least once per week | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | Yes | No | Yes
Consider catch basin modification opportunities to allow FCD installation | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | Yes | Yes | Yes
Consider catch basin modification opportunities to allow FCD installation | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | No | No | No | Yes | No | Yes | No | Yes
Contract for regenerative air street sweeping/vacuuming | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | Yes | No | Yes
Contract for regenerative air vacuums | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | Yes | No | Yes
Contract for Regenerative Air Vacuums | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | Yes | Yes
Contract for street sweeping/vacuuming at or below 5 MPH with parking enforcement oversight | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | Yes | No | Yes
Contract for Street Sweeping/Vacuuming at or below 5 mph with parking enforcement oversight | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | Yes | No | Yes
Contract with solid waste franchisee to provide bins limited opening lids of commercial and food outlets | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | No | No | Yes
Develop and enforce impervious surfaces pet waste ordinance | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes
Develop and enforce trash bin source control ordinances of commercial and food outlets | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | No | No | Yes
Develop and implement targeted outreach efforts through City/SEAACA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes
Develop ordinance controlling pet waste on impervious surfaces | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | No | Yes
Develop pollutants of concern (POC) source control outreach program | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes
Develop pollutants of concern (POC) source control program | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | Yes | Yes | Yes | Yes
Develop targeted City/SEAACA pet waste outreach materials | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | No | Yes
Develop targeted City/SEAACA pet waste outreach materials | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes
Develop targeted E. coli control outreach program and materials | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | Yes | Yes
Develop targeted outreach effort related to bacterial discharges of commercial and food outlets | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes
Develop targeted pet waste information of city website or alternative media | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes
E Coli Control | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes
E.coli Source Control | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | No | No
Enhance catch basin full capture device (FCD/CPS) cleaning | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | No | No | No | Yes | No | No | Yes | Yes
Enhance catch basin full capture device (FCD/CPS) cleaning | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | No | No | No | Yes | No | Yes | No | Yes
Enhance enforcement of trash bin closure (E. coli) source controls | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | Yes | Yes
Enhance IC/ID enforcement & follow up | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | No | Yes
Enhance Illicit Connection/Discharge (IC/ID) enforcement & follow up | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | No | No | No | No | No | No | No | Yes
Enhance the extent, timing, and/or frequency of catch basin and storm drain cleaning | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | Yes | No | Yes
Enhanced IDDE Enforcement | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | Yes | No
Enhanced Industrial/Commercial Inspections | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | Yes | No
Expand street sweeping/vacuuming to include arterial medians | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | Yes | No | Yes
Expand the use of alternative media outlets, including city website for pet waste | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes
Fat, Oil, and Grease Inspections | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | Yes | No
FCD and CPS Cleaning | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | No | No | Yes
FOG Control Inspections | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | No | No | No | Yes | No | No | No | Yes
Gateway COG PATH NGO Partnership | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | Yes | No | No | No | No | No | Yes | No
Gateway COG PATH NGO Partnership | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | No | No | No | No | No | Yes | No | Yes
IC Facility Inspectors | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | No | No | No | Yes | No | No | No | No
Identify catch basin and storm drain cleaning modification opportunities and consider implementation | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | Yes | No | Yes
Identify cleaning frequency for catch basins with CPS or ARS | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | Yes | No | Yes
Identify cleaning frequency for catch basins with CPS or ARS | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | Yes | No | Yes
Identify IC/ID modification opportunities and consider implementation | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes
Identify IC/ID program opportunities and consider implementation | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | No | Yes
Illicit Connection and Discharge Program | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes
Implement enforcement ordinances and prompt follow up inspections for Illicit Connection/Discharge (IC/ID). | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes
Industrial and Commercial Inspections | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes
Industrial and Commerical Inspections | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes
Industrial/Commercial (I/C) inspectors to provide list of watershed TMDL POCs (e.g. trash, zinc, E.coli bacteria) | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes
John Anson Ford Park | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Safe, Clean Water | Yes | Yes | No | Yes | No | Yes | No | No
Modify solid waste disposal contracts to provide limited opening lids | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | No | Yes
Parking Enforcement | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | Yes | Yes
PATH Partnership | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes
Pet Waste Ordinance | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes
Pet Waste Ordinance | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | No | No
Pet Waste Ordinance | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | Yes | No
Pet Waste Outreach | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes
POC Source Control Program | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | No | No | No | No | No | No | Yes | No
POC Source Control Program | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | No | Yes
POC Source Control Program | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | No | No | Yes | No | No | No | No | No
Public Information and Participation Program | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | No | Yes
Public Information and Participiation Program | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | No | Yes
Regenerative Air Vacuums | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | Yes | No | No
Regenerative Air Vacuums | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | Yes | Yes
Rosewood Park | Bell, Huntington Park, Cudahy, Maywood, Bell Gardens, Vernon | Not Applicable | Not Applicable | Not Applicable | Not Applicable | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Solid Waste Disposal Contract | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | No | Yes
Street vacuum arterial medians | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | Yes | Yes
Street vacuum arterial medians | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | Yes | No | Yes
Street Vacuuming | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | Yes | Yes
Street Vacuuming | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | Yes | No | No
Street Vacuuming Parking Enforcement | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | Yes | No | No | No | No | Yes | Yes | No
Study of opportunities to enhance or modify education and outreach program for implementation | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes
Trash Bin Closure Enforcement | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | No | Yes
Trash Bin Closure Source Control | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Other (non-Safe, Clean Water) | Yes | No | No | No | No | No | Yes | No
Utilize alternative media to support POC source control program | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes
Utilize alternative media to support POC source control program | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | Yes | Yes | Yes | Yes
Utilize Gateway COG People Assisting the Homeless (PATH) NGO Partnership | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | No | No | Yes
Utilize Gateway COG People Assisting the Homeless (PATH) NGO Partnership | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | Yes | Yes
Utilize I/C facility inspectors to identify POCs | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | No | Yes
Utilize Indutrial/Commercial (I/C) facility inspectors to identify POCs | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | No | No | No | No | No | No | No | Yes
Utilize parking enforcement to maximize vacuum performance | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | No | No | Yes | Yes | Yes
Utilize parking enforcement to maximize vacuum performance | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | Yes | No | Yes
Utilize signage/parking enforcement to maximize vacuum performance | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Yes | No | No | Yes | No | Yes | No | Yes
Veterans Park Yard | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Safe, Clean Water | Yes | No | No | Yes | No | No | No | No
Warehouse (Exist) | Not Applicable | Not Applicable | 0 | 0 | Not Applicable | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes